## Sheet1
User Story | Description | Points | Due Date | Mon | Tue | Wed | Thus | Fri | Complete?
1 | As a player I would like to play this game in my browser (cross platform) | 1 | 2017-09-22 | 3hr |  |  |  |  | Y
2 | As a player I would like to see the UI (new game/quit game) | 3 | 2017-09-22 |  | 30Min |  |  |  | Y
3 | As a player I would like to move my character in a 2 dimensional environment | 3 | 2017-09-22 |  | 1hr |  |  |  | Y
4 | As a player I would like a clear definition of player and NPC | 1 | 2017-09-22 | 1hr | 20Min |  |  |  | Y
5 | As a player I should get feedback when I get hit/lose life | 3 | 2017-09-22 |  |  | 3hr | 1hr | 4hr | N
6 | As a player I want to define the level's boundaries | 2 | 2017-09-22 | [5 empty] | N
7 | As a player I want to know when I have won/lost the game | 2 | 2017-09-22 | [5 empty] | N
8 | As a player I should choose where to start or to change the difficulty | 5 | 2017-09-22 | [5 empty] | N
| Total: | 20